## Ford_CW43
[6 empty] | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28
Prio | Unique ID | Task name | Work complete | Estimated effort | Real effort | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | Estimated start date | Estimated end date | Comment
|  | Daily Meeting |  |  |  | 1 | 1 | 1 | 1 | 1
2 | 15820 | Loop 6: HMI Changes: ClockandDate |  | 6 | [5 empty] | 6
2 | 16517 | Loop7 S0 CF#36263 Cluster doesn´t show dashes in TPMS screen when value is unknown / invalid |  | 4 | [5 empty] | 2

## Ford_CW44
[6 empty] | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04
Prio | Unique ID | Task name | Work complete | Estimated effort | Real effort | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | Estimated start date | Estimated end date | Comment
|  | Daily Meeting |  |  |  | 1 | 1 |  | 1 | 1
2 | 15820 | Loop 6: HMI Changes: ClockandDate |  | 7 |  | 6 | 4 | 3 | 7 | ?
2 | 16517 | Loop7 S0 CF#36263 Cluster doesn´t show dashes in TPMS screen when value is unknown / invalid | 90% | 3 |  | 1 |  |  | 0
| 20521 | [Loop8](S0) #41234 TPMS INTUITIVE : For S0 cluster "--" is displayed instead of "---" for PSI & KPA units and … | 90% | 5 |  |  | 3 | 1 | 0
| 20517 | [Loop8](S0) #36135 Header name appear when w381 is activated on S0, Menu> Advance Settings> Maintenance,> Tire pressure | 0% | 6 |  |  |  | 4 | 0
| 20576 | Maintenance - Menu header must be cleared if a warning is displayed | 0% | 6 |  |  |  |  | 0 | 1

## Ford_CW45
[6 empty] | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11
Prio | Unique ID | Task name | Work complete | Estimated effort | Real effort | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | Estimated start date | Estimated end date | Comment
|  | Daily Meeting |  |  |  | 1 | 1 | 1 | 1 | 1
2 | 15820 | Loop 6: HMI Changes: ClockandDate | 100% | 7 |  | 4 | 4
| 20576 | Maintenance - Menu header must be cleared if a warning is displayed | 100% | 6
| 20521 | [Loop8](S0) #41234 TPMS INTUITIVE : For S0 cluster "--" is displayed instead of "---" for PSI & KPA units and … | 90% | 5 |  | 3 | 3
| 20517 | [Loop8](S0) #36135 Header name appear when w381 is activated on S0, Menu> Advance Settings> Maintenance,> Tire pressure | 100% | 6
|  | test 20521 | 100% | 6 |  |  |  | 7 | 7 | 7
|  | sort widgets according to ID | 100% | 6

## Ford_CW46
[6 empty] | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-19
Prio | Unique ID | Task name | Work complete | Estimated effort | Real effort | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | Estimated start date | Estimated end date | Comment
|  | Daily Meeting |  |  |  | 1 | 1 | 1 | 1 | 1
6.3 | 20825 | [Loop6.3](S0) #41580 V362MCA - TPMS reset | 80% | 8 |  | 7 | 7 | 5 | 5
| 20824 | [Loop8.2](S0) TPMS reset overtake | 80% | [6 empty] | 7
6.3 | 20518 | [Loop6.3](S0) #41234 TPMS INTUITIVE : For S0 cluster "--" is displayed instead of "---" for PSI & KPA units and … | 80% |  |  |  |  | 2 | 2
Ford | 20591 | [Loop8][S0] #41976 Global Clock Leap Year issue | 0% |  | 10
Ford | 20824 | [Loop8](S0) #41580 V362MCA - TPMS reset | 0% |  | 0
| 20686 | Loop8: S0: MyKey speedlock PopUp frame not according to QT simulation | 0% |  | 6
| 20832 | [Loop8][S0] Missing leading Zero in Clock Menu (Time) | 0% |  | 8

## Ford_CW47
[6 empty] | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25
Prio | Unique ID | Task name | Work complete | Estimated effort | Real effort | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | Estimated start date | Estimated end date | Comment
|  | Daily Meeting |  |  |  | 1 | 1 | 1 | 1 | 1
6.3 | 20825 | [Loop6.3](S0) #41580 V362MCA - TPMS reset | 80% | 8
6.3 | 20518 | [Loop6.3](S0) #41234 TPMS INTUITIVE : For S0 cluster "--" is displayed instead of "---" for PSI & KPA units and … | 80%
Ford | 20591 | [Loop8][S0] #41976 Global Clock Leap Year issue | 10% | 10 |  |  | 7 | 3
Ford | 20824 | [Loop8](S0) #41580 V362MCA - TPMS reset | 100% | 0 |  | 7
| 20686 | Loop8: S0: MyKey speedlock PopUp frame not according to QT simulation | 0% | 6 |  |  |  | 4 | 2
| 20832 | [Loop8][S0] Missing leading Zero in Clock Menu (Time) | 0% | 8 |  |  |  |  | 5 | 4